## Roadmap
VoiceForge — Build Roadmap & Task Tracker
Mark status per task · Enter actual hours · Dashboard auto-updates
| Task | Description | Est. Hours | Status | Actual Hrs | ✓ | Notes
Phase 1 — Local GPU Setup (Orpheus TTS)
| Verify CUDA + drivers | nvidia-smi → RTX 5070 Ti + CUDA 13.1 confirmed ✓ | 0.5 | Done
| Install PyTorch cu128 | pip install torch==2.8.0+cu128 torchaudio torchvision --index-url cu128 ✓ | 0.5 | Done
| Verify PyTorch sees GPU | python -c 'import torch; print(torch.cuda.is_available())' → True ✓ | 0.5 | Done
| Install LM Studio | Download from lmstudio.ai, install on Windows ✓ | 0.5 | Done
| Download Orpheus Q4_K_M GGUF model | Search orpheus-3b-0.1-ft in LM Studio, download isaiahbjork Q4_K_M (~2GB) ✓ | 1 | Done
| Start LM Studio local server | Toggle server ON in Developer tab → port 1234 ✓ | 0.5 | Done
| Clone orpheus-tts-local repo | git clone https://github.com/isaiahbjork/orpheus-tts-local ✓ | 0.5 | Done
| Install repo dependencies | pip install torch numpy sounddevice requests snac ✓ | 0.5 | Done
| Run example.py — basic TTS test | python example.py → Tara + Leo voices generated ✓ | 0.5 | Done
| Test emotion tags | <laugh> <sigh> <whisper> <chuckle> <gasp> all working ✓ | 0.5 | Done
| Listen and verify audio quality | Verify voices sound natural and emotions render correctly ✓ | 0.5 | Done
| Install faster-whisper for STT | pip install faster-whisper, test transcription on wav file | 1 | Done
| Test STT on generated audio | Transcribe Orpheus output, verify accuracy | 0.5 | Done
| VRAM check | nvidia-smi during generation → verify under 12GB limit | 0.5 | Done
Phase 2 — FastAPI Wrapper (Orpheus Bridge)
| Understand LM Studio API structure | LM Studio exposes OpenAI-compatible API at localhost:1234 | 0.5 | Done
| Install FastAPI + uvicorn | pip install fastapi uvicorn python-multipart soundfile | 0.5 | Done
| Build /tts endpoint | POST text+voice → calls LM Studio:1234 → decodes SNAC tokens → returns .wav | 2.5 | Done
| Integrate SNAC decoder | pip install snac → decode Orpheus token output into audio waveform | 1.5 | Done
| Build /tts/voices endpoint | GET /voices → returns list of 8 available Orpheus voices | 0.5 | Done
| Build /stt endpoint | POST audio file → faster-whisper transcribes → returns JSON transcript | 1.5 | Done
| Add emotion tag validator | Whitelist valid tags: laugh,sigh,whisper,chuckle,gasp,cough,groan,yawn | 1 | Done
| Add API key auth middleware | Validate Bearer token on all routes before processing | 1 | Done | 1
| Add char count + credit deduction | Count input chars → call Express credit API → deduct before generating | 1 | Done | 1
| Stream audio response to client | Pipe generated wav bytes directly to response, set audio/wav header | 1.5 | Done | 1
| Test all endpoints via Postman | TTS → STT → voices → verify auth, credits, audio quality | 1.5 | Done | 1
| Expose via ngrok for frontend dev | ngrok http 8000 → public URL for Next.js frontend testing | 0.5 | Done | 1
| Write Dockerfile for production | Orpheus GGUF + faster-whisper + FastAPI in one Linux image | 2 | Done | 1
| Test Docker image locally | docker build + run → verify same behavior as local server | 1 | Done | 1
| Document all API routes | Write endpoint docs: params, responses, error codes | 1 | Done | 1
Phase 3 — Express Backend
| Init Node.js + Express project | npm init, install express cors dotenv | 0.5 | Not Started
| Setup PostgreSQL + Prisma | neon.tech free DB + prisma init | 1.5 | Not Started
| Design DB schema | Users, ApiKeys, Credits, UsageLogs tables | 1.5 | Not Started
| Run prisma migrate | Push schema to DB, verify tables created | 0.5 | Not Started
| Build JWT auth (register/login) | POST /auth/register + /auth/login endpoints | 2 | Not Started
| Build API key system | Generate, hash, validate API keys per user | 2 | Not Started
| Build credit system | Deduct credits per char on each TTS request | 2 | Not Started
| Integrate Razorpay billing | Create order, verify payment, top up credits | 3 | Not Started
| Build proxy route to FastAPI | Express forwards TTS/STT calls to Python server | 1.5 | Not Started
| Add rate limiting (express-rate-limit) | Prevent abuse, per API key limits | 1 | Not Started
| Build usage analytics endpoint | GET /usage → chars used, calls made, credits left | 1.5 | Not Started
| Add BullMQ job queue | Queue heavy requests, prevent server overload | 2 | Not Started
| Write .env config + error handlers | Clean error responses, env validation | 1 | Not Started
| Test full backend flow via Postman | Auth → get key → TTS call → credit deducted | 2 | Not Started
Phase 4 — Next.js Frontend
| Init Next.js 14 project | npx create-next-app, add Tailwind + shadcn/ui | 1 | Not Started
| Build landing page | Hero, pricing section, feature list, CTA | 4 | Not Started
| Build auth pages (login/register) | Forms with validation, connect to Express auth | 2 | Not Started
| Build dashboard layout | Sidebar nav, header with credit balance | 2 | Not Started
| Build Voice Studio UI | Text input, voice selector, generate button, player | 4 | Not Started
| Build API key manager page | Create/delete/copy keys, usage per key | 2 | Not Started
| Build credit & billing page | Current balance, top-up with Razorpay, history | 3 | Not Started
| Build usage analytics page | Charts: chars/day, calls/day, credit burn rate | 3 | Not Started
| Connect all pages to Express API | Axios/fetch calls, auth headers, error states | 3 | Not Started
| Add loading states + error handling | Skeletons, toasts, retry logic | 2 | Not Started
| Mobile responsiveness | All pages work on phone/tablet | 2 | Not Started
Phase 5 — Integration & QA
| Full E2E flow test | Register → top up → generate TTS → download | 2 | Not Started
| Voice clone E2E test | Upload audio → clone → generate → verify quality | 1.5 | Not Started
| STT E2E test | Upload audio → transcript → verify accuracy | 1 | Not Started
| Credit deduction accuracy test | Verify chars counted correctly per request | 1 | Not Started
| API key auth test | Valid key works, invalid rejected, expired handled | 1 | Not Started
| Load test FastAPI server | Send 10 concurrent requests, check stability | 1.5 | Not Started
| Fix bugs from testing | Address all issues found in E2E tests | 3 | Not Started
| Security review | Check for exposed secrets, SQL injection, XSS | 2 | Not Started
Phase 6 — Production Deployment
| Deploy Next.js to Vercel | Connect GitHub repo, set env vars, deploy | 1 | Not Started
| Deploy Express to Railway | Dockerfile or buildpack, set env vars, test | 1.5 | Not Started
| Setup Neon PostgreSQL prod DB | Create prod DB, run migrations, seed data | 1 | Not Started
| Setup Upstash Redis prod | Create Redis instance, connect to Express | 0.5 | Not Started
| Deploy FastAPI to RunPod Serverless | Push Docker image, configure GPU endpoint | 2 | Not Started
| Configure RunPod auto-scaling | Set min/max workers, idle timeout settings | 1 | Not Started
| Update all env vars for production | API URLs, secrets, Razorpay live keys | 1 | Not Started
| Setup custom domain | Point domain to Vercel, SSL auto-configured | 1 | Not Started
| Final production smoke test | Full flow on live URL with real Razorpay | 1.5 | Not Started
| Setup error monitoring (Sentry) | Catch prod errors in Express + Next.js | 1.5 | Not Started
| Go live — share with first users | Post in communities, get first feedback | 1 | Not Started

## Dashboard
VoiceForge — Build Dashboard
Live progress tracker — update status on Roadmap sheet to refresh
| TOTAL TASKS |  | COMPLETED |  | IN PROGRESS
| tasks total |  | tasks done ✓ |  | tasks active
| EST. TOTAL HOURS |  | HOURS LOGGED |  | % COMPLETE
| hours planned |  | actual hours |  | completion rate
Phase Progress
| Phase |  | Total | Done | Est Hrs | Progress
| Phase 1 — Local GPU Setup (Orpheus TTS) |  | 14
| Phase 2 — FastAPI Wrapper (Orpheus Bridge) |  | 15
| Phase 3 — Express Backend |  | 14
| Phase 4 — Next.js Frontend |  | 11
| Phase 5 — Integration & QA |  | 8
| Phase 6 — Production Deployment |  | 11
TOTAL
Monthly Cost Tracker (Serverless GPU)
| Service | Provider | Plan | INR/month | Notes | Notes
| GPU Server | RunPod | RTX 4090 Serverless |  | Edit ↑ based on actual usage | Edit ↑ based on actual usage
| Express Backend | Railway | Hobby | 400 | Fixed monthly | Fixed monthly
| Next.js Frontend | Vercel | Hobby | 0 | Free tier | Free tier
| PostgreSQL | Neon | Serverless Free | 0 | Free up to 0.5GB | Free up to 0.5GB
| Redis | Upstash | Free | 0 | 10k commands/day free | 10k commands/day free
| Payments | Razorpay | Pay per txn | 0 | 2% per transaction | 2% per transaction
| Domain | Any registrar | Annual | 0 | ~₹800/yr = ₹67/mo | ~₹800/yr = ₹67/mo
TOTAL (excl GPU)

## Schedule
VoiceForge — Weekly Build Schedule
Plan your weekly hours · Each cell = hours you'll work on that day · Adjust to your own pace
| Phase / Task | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Total Hrs
| Phase 1 — Orpheus GPU Setup | 1 | 1 | 1 | 1 | 0.5 | 2 | 1
| Phase 2 — FastAPI Wrapper | 2 | 2 | 2 | 2 | 2 | 3 | 3
| Phase 3 — Express Backend | 2 | 2 | 2 | 2 | 2 | 3 | 2
| Phase 4 — Next.js Frontend | 2 | 2 | 2 | 2 | 2 | 3 | 2
| Phase 5 — Integration & QA | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2.5 | 2
| Phase 6 — Deployment | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 2 | 1.5
TOTAL HOURS / DAY
Tips: Phase 1 is mostly complete — you already have Orpheus running with emotion tags. Phase 2 (FastAPI wrapper) is the next big task. Total ~105hrs ≈ 4-5 weeks part-time.